## Task Board
L’ÉDITION MAGAZINE — Task Tracker
Plan and track all development tasks across Backend, Frontend, Database, and Design.
Total Tasks: 0 |  |  | To Do: 0 |  |  | In Progress: 0 |  |  | Done: 0 |  |  | Blocked: 0
Task ID | Sprint / Phase | Category | Task Title | Description | Acceptance Criteria | Assigned To | Priority | Status | Est. Hrs | Actual Hrs | Start Date | Due Date
TSK-001
TSK-002
TSK-003
TSK-004
TSK-005
TSK-006
TSK-007
TSK-008
TSK-009
TSK-010
TSK-011
TSK-012
TSK-013
TSK-014
TSK-015
TSK-016
TSK-017
TSK-018
TSK-019
TSK-020
TSK-021
TSK-022
TSK-023
TSK-024
TSK-025
TSK-026
TSK-027
TSK-028
TSK-029
TSK-030
TSK-031
TSK-032
TSK-033
TSK-034
TSK-035
TSK-036
TSK-037
TSK-038
TSK-039
TSK-040
TSK-041
TSK-042
TSK-043
TSK-044
TSK-045
TSK-046
TSK-047
TSK-048
TSK-049
TSK-050

## Sprint Planner
Sprint Planning Overview
Phase | Name | Timeline | Key Deliverables
Phase 1 | Project Setup | Week 1–2 | GitHub repo, Supabase project, Next.js + .NET boilerplate, folder structure, CI/CD pipelines
Phase 2 | Database & Auth | Week 3–4 | All 9 tables in Supabase, RLS policies, Supabase Auth, JWT in .NET API, seed data
Phase 3 | Public Magazine | Week 5–7 | Homepage, article detail, category pages, bookmarks, newsletter, privacy policy, author profiles
Phase 4 | Author Portal | Week 8–10 | Login, dashboard analytics, article editor, draft/review/published tabs, preview, profile settings
Phase 5 | Admin Portal | Week 11–13 | Admin login, editorial review, content manager, author management, audience, site settings, profiles
Phase 6 | Testing & QA | Week 14–15 | Netlify branch QA, isolated Supabase QA DB, cross-browser, mobile testing, issue triage
Phase 7 | Production Deploy | Week 16 | Vercel Pro + Azure S1 + Supabase Pro, custom domain, SSL, monitoring, smoke test, go-live

## Category & Status Guide
Task Category & Status Guide
TASK CATEGORIES
Label | Colour Tag | Meaning
Frontend | Frontend | Next.js pages, React components, Tailwind CSS, routing, layout
Backend | Backend | ASP.NET Core API controllers, services, middleware, DTO models
Database | Database | Supabase tables, RLS policies, migrations, seed data, queries
Auth | Auth | Supabase Auth setup, JWT tokens, OAuth, session management
DevOps | DevOps | GitHub, CI/CD pipelines, Netlify, Vercel, Azure deployments
Design | Design | UI mockups, image assets, typography, icon system, branding
Testing | Testing | Manual QA, bug verification, cross-browser, mobile, regression
Docs | Docs | README, API documentation, Excel specs, onboarding guides
TASK STATUSES
Label | Colour Tag | Meaning
To Do | To Do | In the backlog. Not yet started.
In Progress | In Progress | A developer is actively working on this right now.
In Review | In Review | PR submitted or QA testing underway — awaiting approval.
Blocked | Blocked | Cannot proceed — waiting on dependency or another team member.
Done | Done | Completed, reviewed, merged, and verified in the target environment.